## Sheet1
COSC1076 ¦ Semester 1 2024
Assignment 2 ¦ Weekly Update Tracking Sheet
|  |  |  | Github Repo Url: | https://github.com/s3658534/APT-Tue-10-30-P6---Group-6
Group Name: | APT-Tue-10-30-P6---Group-6
Group Member: | Shaoguan Ye |  | Progress Classes: | Ahead
Group Member: | Gayeong Lee |  |  | On-track
Group Member: | Heath Yates |  |  | Behind
Way Behind
Tutor: | Dale
Class: | Tuesday 12:30
|  | Week 8 | Goals | Tutor Notes | Individual Updates | Shaoguan Ye | Gayeong Lee | Heath Yates | D
|  |  | Group Formed |  | Weekly Contribution | Created group and github page
|  |  | MS Team created |  | Issues
|  |  | Git Repo created |  | Other Notes
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Individual Updates | Shaoguan Ye | Gayeong Lee | Heath Yates | D
|  |  | First Team Meeting |  | Weekly Contribution | Planned the basic structure of the program | Planned the basic structure of the program | Did requirements 2 and 9
|  |  | Assign each member 4 requirements |  | Issues | Did requirements 5 | Did requirement 6 and 8 | Could not attend first meeting
|  |  | Work on needed requirements for demonstration |  | Other Notes
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Individual Updates | A | B | C | D
|  |  | Complete all requirements for code submission |  | Weekly Contribution | Did requirements 3 4 11. | Did requirement 7 | Did requirements 10 and 12, did tests for requirements 2 and 9,Error handled both files when reading
|  |  | Error handle code properly |  | Issues | Bug fixed for purchasing meal (req5) | Fix data structure and bug
|  |  | Create tests for all reqirements |  | Other Notes |  |  | First "demo" has this week, next one is next week
|  | Progress | On-track
|  | Week 11 | Goals | Tutor Notes | Individual Updates | A | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | test case for Req 5 is done | Tast cases for req 6 and 7 is done | Finished code along with final tests, did demo on tuesday.
|  |  | Demonstration |  | Issues | Bug fixed for req 3 4 5 | Add pipe symbol removed output in req7
[5 empty] | Other Notes |  |  | Will wait to write the report as it is due in weeks
Final Tests
|  |  | Group Report Written | not done
|  | Progress | On-track
Note on D22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Note these are just some random thought on "setting goals". Feel free to set whatever goals your group thinks appropriate here...